## 3000
3000 To Do
Name | Status | Priority | Timeline - Start | Timeline - End | Dependent On
Law enforcement contact | In Progress | Critical ⚠️️ | 2025-09-27 | 2026-04-30
Project vision | Done | High | 2025-10-13 | 2025-10-24 | Law enforcement contact
Project planning | Done | Medium | 2025-10-13 | 2025-10-24 | Project vision, Risk management
Risk management | Done | High | 2025-10-13 | 2025-10-24 | Law enforcement contact, Project vision
Scope finalisation and research questions | Working on it | High | 2025-10-20 | 2025-11-10 | Law enforcement contact, Project vision, Project planning
Search and collect secondary sources | Not Started | Low | 2025-11-10 | 2025-12-08
Literature review and writing | Not Started | Medium | 2025-11-17 | 2025-12-22 | Search and collect secondary sources
Methodology review and writing | Not Started | High | 2025-12-08 | 2026-01-12 | Scope finalisation and research questions, Literature review and writing, Search and collect secondary sources, Project vision
Optional interviews | Not Started | Low | 2026-01-12 | 2026-01-19 | Law enforcement contact
Case study analysis | Not Started | High | 2026-01-19 | 2026-02-02 | Law enforcement contact
Link case findings to literature review | Not Started | High | 2026-02-02 | 2026-02-23 | Case study analysis, Literature review and writing
Poster | Not Started | Medium | 2026-03-02 | 2026-03-16 | Project vision, Scope finalisation and research questions, Literature review and writing, Case study analysis
Write findings and discussion | Not Started | Medium | 2026-02-23 | 2026-03-16 | Literature review and writing, Methodology review and writing, Case study analysis, Link case findings to literature review
Conclusion, reflection and recommandations writing | Not Started | Medium | 2026-03-16 | 2026-04-06 | Write findings and discussion, Link case findings to literature review
Final review | Not Started | Low | 2026-04-27 | 2026-05-04
Reflection and professional development | Not Started | Medium | 2026-05-04 | 2026-05-15 | Law enforcement contact, Conclusion, reflection and recommandations writing, Case study analysis
|  |  | 2025-09-27 | 2026-05-15